## Slide 1: Project Management (in Software Engineering)
An Introduction

## Slide 2: Getting Started
Projects:
  A project is a one-time effort to achieve a particular goal, subject to time and/or budget constraints
In Contrast:
  Ongoing activities and/or activities that do not have constraints are not projects
Management:
  Management is the activity of assembling, directing, and/or supporting human and other resources in achieving substantial goals

## Slide 3: Management Issues
Scope:
  The work to be done in the project
Time:
  A constraint (and, hence, a resource to be monitored)
Cost:
  A constraint (and, hence, a resource to be monitored)
Project Management Iron Triangle
  Brooks’ Law states that adding programmers
  to a late project makes it later.
Notes: It takes some time for the people added to a project to become productive.
Communication overheads increase as the number of people increases
Limited divisibility of tasks

## Slide 4: Management Issues (cont.)
Quality:
  Either a part of the goal of the project or a constraint
Resources:
  Things that must be "obtained" and ready when needed in order to complete the project
Risks:
  Uncertain conditions/circumstances that have negative consequences

## Slide 5: Management Activities
Plan:
  Set goals, establish constraints, set requirements, determine tasks, estimate costs, formulate schedules, assign resources, manage risks
Execute:
  Acquire resources, train/educate, establish processes
Control:
  Collect data, analyze data, report on progress, adjust scope/schedule/budget
Lead:
  Motivate, facilitate, resolve conflicts, remove obstacles

## Slide 6: Management Responsibilities
Traditional Processes:
  Management responsibilities are assigned to project managers who are given the responsibility and authority to collect data, make decisions, and control resources
Agile Processes:
  Reduce the need for oversight and distribute authority and responsibility for most activities to the team, though there are exception (e.g., in Scrum leadership activities are the province of the Scrum Master)
Notes: Section 2

## Slide 7: Planning
Terminology:
  Milestone - any significant event in a project
  Deliverable - any document, program, data, service, or object produced for an internal or external customer
  Scheduling - deciding when a task will occur
  Resource Allocation - deciding which people/resources will be used for which tasks
Traditional Processes:
  Most planning activities occur "up front"
Agile Processes:
  Planning occurs at the start of each increment
Notes: Section 1

## Slide 8: Planning (cont.)
Organizing Deliverables:
  Work Breakdown Structure (WBS) - a hierarchical decomposition of the work needed to produce deliverables (where the leaf nodes are called work packages requiring between 8 and 80 person-hours)
Scheduling Tools:
  Program Evaluation and Review Technique (PERT)
  Critical Path Methods (CPM)
  Gantt Charts

## Slide 9: Planning (cont.)
An Example of a Work Breakdown Structure for the Product HomeSafe

## Slide 10: Execution
Traditional Processes:
  Project managers are responsible for and have the authority needed for execution activities
Agile Processes:
  The team is responsible for and has the authority needed for execution activities

## Slide 11: Control
Traditional Processes:
  Project managers are responsible for monitoring and making changes to the plan (though the changes should be made in consultation with stakeholders)
Agile Processes:
  The team uses burn charts to track progress and makes changes usually at the end of an increment (e.g., during the Sprint Retrospective in Scrum)

## Slide 12: Leadership
Traditional Processes:
  Project managers are responsible for leadership activities
Agile Processes:
  Vary in who has responsibility for leadership activities (e.g., in Scrum it is the Scrum Master)

## Slide 13: Project Progress Tracking

## Slide 14: Motivation
The Objective:
  Track the progress of a project
Some Obvious Metrics:
  Size
  Time
  Money

## Slide 15: A Common Mistake
An Obvious Way to Proceed:
  Compare the actual amount of time used or money expended to the planned amount (e.g., the plan was that the project would require 80 hours and we have used 40 hours so we have completed 50% of the project)
Shortcomings of this Approach:
  The planned amount (whether measured in time or money) may have been overestimated or underestimated
  The planned drawdown rate may not have been linear over time (so, just because we have spent 50% of the budget may not mean that the project is 50% complete, even if the original estimate was correct)

## Slide 16: A Better Approach - Earned Value Analysis
The Concept:
  Use a quantifiable measure of progress (called the value)
  Compare the planned value with the earned value over time
The Process:
  Before the project starts, use the project plan to calculate the planned value for each period, Vt*
  While the project is underway, calculate the actual value for each period, Vt
  Compare over time

## Slide 17: Earned Value Analysis (cont.)
Possible Measures of Value:
  The number of completed features
  The normalized number of completed features (sometimes called story points)
  The monetary business value of completed features
Metrics:
  Schedule Variance (in value units not time units):
  Cost Variance: ∑Tt=0Vt−∑Tt=0Ct where Vt is measured in dollars and Ct denotes the costs incurred during period t
  Cost Performance Index:

## Slide 18: Earned Value Analysis (cont.)
An Example

## Slide 19: Burn Charts for Earned Value Analysis
Purpose:
  Show the planned and earned value over time
Types:
  Burn-up charts show how much value has been completed
  Burn-down charts show home much value remains to be completed

## Slide 20: An Example Burn-Up Chart
The State of the Project after the 7th Sprint:
Interpretation:
  13 sprints are planned.
  The number of story points was increased from 350 to 425 to 450.
  Since story points are a measure of effort and the team completes work at a constant rate, the dashed line shows expectations.
  The project started well but has fallen behind.

## Slide 21: An Example Burn-Down Chart
The State of the Project during a 15-day Sprint:
Interpretation:
  The sprint backlog started with 31 story points worth of PBIs.
  At the end of day 2, PBIs with a total size of 5 story points had been completed.
  At the end of day 3, PBIs with a total size of 2 story points had been completed.
  No more story points were completed until day 5, at which time 2 were completed.