## Sheet1
Section #: | 2022-01-04
Team Name: | Big Data Energy
Name | Assigned Tasks | Total # of Planned Hours | When is it due? | Completion Status | Total # of Actual Hours Worked | Passed testing? | Remarks
Example | #20, #26 | 5 | #20: 12pm, 9/25 #26: 5pm, 9/25 | #20: 90191fb1, 11pm, 9/24 #26: 66c23b39, 8pm, 9/25 | 7 | #20: Yes, passed testcase1 #26: Partially passed Testcase2 | None
Bryan Burch | BDE-27 | 4 | 10am 10/4 | done | 4 | Yes | none
Daniel Smagly | BDE-28 | 4 | 10am 10/4 | done | 4 | Yes | had to watch some videos
Jeffrey de Jesus | BDE-29 | 4 | 10am 10/4 | done | 4 | Yes | very straight forward
Christopher Allen | BDE-30 | 4 | 10am 10/4 | done | 3 | Yes | none
Santiago Bermudez | BDE-31 | 4 | 10am 10/4 | done | 3 | Yes | none
Julian Hernandez | BDE-32 | 4 | 10am 10/4 | done | 5 | Yes | none
Travis Hammond | BDE-43 | 4 | 10am 10/4 | done | 5 | Yes | went down a rabbit hole
Kenta Miyahara | BDE-44 | 4 | 10am 10/4 | done | 4 | Yes | none