## Sheet1
Section #: | 2022-01-04
Team Name: | Big Data Energy
Name | Assigned Tasks | Total # of Planned Hours | When is it due? | Completion Status | Total # of Actual Hours Worked | Passed testing? | Remarks
Example | #20, #26 | 5 | #20: 12pm, 9/25 #26: 5pm, 9/25 | #20: 90191fb1, 11pm, 9/24 #26: 66c23b39, 8pm, 9/25 | 7 | #20: Yes, passed testcase1 #26: Partially passed Testcase2 | None
Bryan Burch | BDE-47 | 4 | 10am, 11/18/2022 | 10am 11/18 | 5 | Yes | none
Daniel Smagly | BDE-45 | 4 | 10am, 11/18/2022 | 4pm 11/17 | 5 | Yes | worked with Travis to get some stuff done
Jeff De Jesus | BDE-35 | 4 | 10am, 11/16/2022 | 12pm 11/16 | 6 | Yes | worked with Chris, needed to research rest apis first
Chris Allen | BDE-34 | 4 | 10am, 11/16/2022 | 12pm 11/16 | 6 | Yes | worked with Jeff, need additional research
Santiago Bermudez | BDE-33 | 4 | 10am, 11/18/2022 | 10am 11/11 | 7 | Yes | woked with Kenta
Julian Hernandez | BDE-36 | 4 | 10am, 11/18/2022 | 10am 11/18 | 9 | Yes | we need to come up with standardized data model
Travis Hammond | BDE-37 | 4 | 10am, 11/18/2022 | 6am 11/17 | 3 | Yes | also helped everyone else with their tasked
Kenta Miyahara | BDE-69 | 4 | 10am, 11/18/2022 | 9pm 11/14 | 7 | Yes | made progress with model inference